1. PROJECT AREA DESCRIPTION & PLANS FOR REVITALIZATION:

Target Area and Brownfields: 1.a. Overview of Brownfield Challenges and Description of Target Area: The tumwata village (former Blue Heron Paper Mill or Site) in historic Oregon City, Oregon (pop. 37,572) is one of the state’s most significant and anticipated brownfield redevelopment opportunities. This 23-acre vacant paper mill sits on a rocky outcrop in the Willamette River adjacent to Willamette Falls—the second largest waterfall by volume in the U.S. and a place of deep cultural and ecological importance. The Site anchors the southern end of downtown Oregon City (Target Area) which extends approximately one mile north of the Site along the river, centered on historic Main Street.

For centuries, the Site and Target Area were a tribal gathering place. In the 1800s, Oregon City was the western terminus of the Oregon Trail, the first incorporated city west of the Rockies, and capital of the Oregon Territory. The hydropower of Willamette Falls powered 19th-century wool, flour, and paper mills, tanneries, and dye works in the Target Area. In the 20th century, downtown Oregon City became commerce and government hub, and Main Street reflected auto-oriented development patterns dominated by gas/service stations and auto dealers. The Blue Heron Paper Mill operated on the Site for 60 years until it closed permanently in 2011.

Despite safety and security measures, the Site forms an unsafe, contaminated eyesore attracting vandalism and crime. For example, in January 2025, trespassers started a massive fire in one of the Site’s vacant buildings. The Site has long been a barrier between the community and the beautiful Willamette River and Falls. Blighted Site conditions cause a ripple effect further into the Target Area, with multiple vacant lots and buildings along Main Street. Oregon Department of Environmental Quality (DEQ) records also show a string of leaking underground storage tank sites in the Target Area. Target Area conditions harm the river ecosystem, deter investment and developer interest, reduce property values, and cause economic stagnation. Despite its scenic location and strong suitability for new residential and commercial uses, contamination constrains redevelopment of the Site with new housing, job opportunities, and the potential to catalyze local and regional economic growth.

In 2019, the Confederated Tribes of Grand Ronde (the Tribe, or CTGR) purchased the Site to steward its redevelopment. In FY21 the Tribe was awarded $800K EPA Brownfield Multipurpose Grant, using the funds to successfully complete environmental sampling, cleanup planning, and preliminary remediation. A FY26 EPA Brownfield Cleanup Grant will cover the remaining cleanup that will advance community-established goals to transform the Site into a regional commercial and recreational destination. Finalizing cleanup of the Site is a powerful opportunity to catalyze Target Area economic revitalization and job creation by promoting cultural tourism, creating recreational opportunities, protecting and restoring the local ecosystem, and reconnecting the community with one of Oregon’s most beautiful and storied natural features.

1.b. Description of the Proposed Brownfield Site: The Site extends along approximately 4,000 feet of the Willamette River, adjoining the River and Falls to the south and west. Railroad tracks and State Hwy 99E form the eastern boundary. Beyond the highway the land rises to a bluff topped by a residential/commercial neighborhood that overlooks the Site. Except for a few isolated areas of vegetation along the river, the Property is paved or occupied by over 50 vacant structures.

Early commercial Site uses included wool, flour, and timber mills, a tannery, soap making, warehouses, and retail businesses. In the 20th century, hydroelectric facilities and the paper mill dominated the Site. The paper mill included extensive operations/process infrastructure including 3 paper machines, a de‐inking plant, bleach houses, dye houses, laundry operations, numerous underground and aboveground storage tanks, two electrical substations, an auto repair shop, a former transformer field, tail races, rail spurs, and large materials storage areas and stockpiles.

In 2019, the Tribe signed a Prospective Purchaser Agreement (PPA) with the Oregon Department of Environmental Quality (DEQ) agreeing to complete assessment and cleanup actions at the Site in exchange for environmental liability protections. A remedial investigation (RI) was completed using the FY21 Brownfield Multipurpose Grant. Primary RI findings included: 1) an estimated 26,500 cubic yards of soil contaminated with arsenic, lead, polycyclic aromatic hydrocarbons and/or dioxins were delineated; and 2) nearly all soil (108,000 cubic yards) within the ecological restoration area of the Site contains the same contaminants at concentrations exceeding DEQ clean fill screening values.

1.c. Reuse Strategy and Alignment with Revitalization Plans: Finalizing Site cleanup will advance a reuse strategy developed through years of collaborative planning. Following the paper mill closure, Oregon City, Clackamas County, Metro (regional planning agency), state agencies, and the Tribe launched the Willamette Falls Legacy Project. This partnership led robust engagement beginning in 2013, involving thousands of Oregonians and resulting in 4 guiding Site reuse principles: economic revitalization, historic and cultural interpretation, public access, and environmental health.

Building on these principles, a Framework Master Plan (2014) established a mixed-use Willamette Falls Downtown zone in the Target Area, replacing the Site’s former industrial zoning. Subsequent efforts included a Catalytic Value Study (2015), a Riverwalk Master Plan (2018), and a Roadmap to Redevelopment (2018), each shaped by input from government, business, nonprofits, and the community. The Tribe advanced these plans in the Tumwata Village Master Plan that hones the vision of the Site. In 2025, the OR Dept. of Land Conservation and Development awarded the Tribe an Achievement in Community Engagement Award for the robust public engagement for the Master Plan, and the Master Plan was formally adopted by the City of Oregon City.

The Master Plan envisions the site as a regional destination with residences, offices, recreational and hospitality amenities, and natural areas. The northern end of the Site will be a vibrant extension of downtown Oregon City, with a green gateway leading to residences, shops, restaurants, and offices connected by pedestrian- and bike-friendly streets. From north to south, the Site’s character will evolve from green urban form to a pedestrian-centered area with gathering and park areas, a hotel, and cafes. Public access to view the Falls will be restored for the first time in over a century.

The redeveloped southern area of the Site, located in a federally designated floodplain, will include stormwater management. The 2024 Grading and Floodplain Plan for the Site outlines balancing cut-and-fill to achieve a net fill reduction and increase floodplain capacity. Strategies may include natural stormwater treatment systems that reduce contaminants and reuse water for irrigation.

The Site reuse strategy aligns with regional plans: Oregon City’s Comprehensive Plan and Downtown Urban Renewal Area prioritize Target Area development for shopping, working, tourism and recreation, social interaction, with pedestrian and bicycle access. The Oregon City Downtown Association 2024 Strategic Plan developed through extensive community surveys identifies underused properties and a lack of riverfront connection as major challenges which this project will address. Clackamas County’s Comprehensive Plan highlights a need for developable land and protecting and supporting natural features and parks. Metro’s 2040 Regional Growth Concept encourages infill development, a healthy economy, and protection of rivers and natural areas.

1.d. Outcomes & Benefits of Reuse Strategy: Metro prepared a Catalytic Value Study of the potential for the transformed Site to stimulate economic development. The study identified a robust set of regional economic and community benefits resulting from the Site’s planned reuse:

Job Creation and Income Tax Revenue: The Site could house up to 926K square feet of commercial space creating an estimated 2,500-5,000 temporary and permanent jobs. This could generate over $40M in annual local income and millions in income tax revenue to be reinvested locally.

Tourism: Oregon is a tourist destination. In 2023, visitor spending topped $14B for the first time in state history. The Catalytic Value Study shows the redeveloped Site could attract 1M visitors annually, creating 931 tourism-related jobs and generating up to $73M in annual visitor spending.

Property Value Impacts: The Site currently reduces nearby property values by $2M. Studies show that brownfield remediation can increase surrounding values by 5–15%, creating homeowner equity and economic stability in the Target Area. Higher property values also make redevelopment financially viable, attracting investment and catalyzing revitalization.

Park/Open Space: Site reuse will include ecological restoration, river access, and a riverwalk. Plans feature a revitalized boat dock, overnight park accommodations, and naturalized trails as well as a community space for markets and destination events framed by historic mill remnants.

Housing: the Oregon City 2021-2041 Housing Needs Analysis projects a need for 50% more housing to accommodate growth. With Oregon City projecting a 50% increase in needed housing, the Site offers a vital opportunity to sustainably expand the housing supply and ease the cost burdens residents face due to current shortages.

Natural Disasters: Heavy winter rains in the Target Area increase flood and landslide risks. By naturalizing a portion of the Site, redevelopment will boost floodplain capacity and enable stormwater capture and reuse. With extreme summer heat, including a 2025 extreme heat warning, re‑greening the Site will help cool the area and lessen energy needs for building cooling.

Renewable energy: Reuse plans include rooftop solar panels on newly constructed buildings.

Strategy for Leveraging Resources:  1.e. Site Characterization: Assessment has been completed and remediation has begun. NO additional assessment is anticipated; however if assessment is needed, funds available to the Tribe are summarized in the table below.

1.f. Site Remediation and 1.g Site Reuse: As a federally recognized Tribe, the CTGR and this project are eligible and well-positioned to leverage funding. Funding historically secured for the Site includes: 2012 Metro bonds for assessment and a Development Opportunity Study; $100K+ in assessment using Metro’s FY16/FY20 EPA Brownfield Assessment Grants; $25K 2019 Business Oregon Grant to develop the scope of environmental assessment/cleanup required by DEQ; and $800K FY21 EPA Brownfield Multipurpose Grant. These investments as well as those highlighted below underscore public confidence in the project’s ability to drive economic opportunity.

| Metro FY20 EPA Brownfield Assessment Grant – Unsecured (Available upon request) |  |
| --- | --- |
| Purpose: Assessment, Reuse Planning | Metro has an active $1.5M regional EPA Brownfield Assessment Grant that includes the Target Area, with funds available for assessment and reuse planning at the site if needed. |
| Oregon DEQ Targeted Brownfield Assessment (TBA) – Unsecured (Available upon request) |  |
| Purpose: Assessment | DEQ’s TBA program can provide further assessment if needed. |
| Business Oregon Brownfield Program – Unsecured (Available upon request) |  |
| Purpose: Assessment, Cleanup, Reuse | The Tribe is eligible for Business Oregon low-interest loans and grants for brownfield assessment, cleanup, and redevelopment planning. The Tribe has had preliminary discussions with Business Oregon regarding a $500K grant that would be dedicated to the cleanup project described in this application. |
| 2022 Congressional Appropriations - $2M SECURED |  |
| Purpose: Cleanup, Reuse | $2M for environmental restoration, demolition, and infrastructure development on the Site. $1M of this grant is eligible for use to fund the cleanup project described in this application. |
| 2009/2017 Oregon State Parks Bond/City of Oregon City Allocation - $12.5M SECURED |  |
| Purpose: Reuse | $12.5M for Riverwalk development on the Site. |
| 2019 Metro Parks and Recreation Bond, Large Scale Community Visions - $20M SECURED |  |
| Purpose: Reuse | $20M for Riverwalk development on the Site |
| FY25 Federal Highway Administration BUILD Grant – Unsecured (Application submitted 2026) |  |
| Purpose: Reuse | $8M for Site roadway and utility infrastructure – the Tribe applied in 2026 and is awaiting notification. |
| CTGR 2024-2029 Transportation Improvement Program – $2M SECURED |  |
| Purpose: Reuse | Funding for road and utility network development. Will be used as required match for above BUILD Grant. |
| FY25 NOAA Transformational Habitat Restoration and Coastal Resilience Grant – Unsecured (Application submitted 2025, awaiting award notification) |  |
| Purpose: Reuse | $10M for increasing flood storage capacity and enhancing off-channel habitat. |
| Oregon Dept. of Land Conservation and Development (DLCD) Green Infrastructure Grant - Unsecured |  |
| Purpose: Reuse | Up to $500K for projects that bring green infrastructure such as stormwater management, greenspace, bioswales, and green roofs. |
| Oregon DLCD Transportation and Growth Management Grants - Unsecured |  |
| Purpose: Reuse | Up to $350K for transportation planning and implementation. |
| Metro Planning & Development and Nature in Neighborhoods Grants - Unsecured |  |
| Purpose: Reuse | Metro offers a variety of grants for reuse planning and habitat restoration. |

1.h. Use of Existing Infrastructure: Revitalization plans include adaptive reuse of selected buildings and structures for use and as sculptural elements in open spaces. Because this project is true infill development adjacent to downtown Oregon City, it will capitalize on the existing infrastructure framework including utility corridors, roadway connections, and service networks. Existing Site infrastructure requires upgrades to meet current capacity and safety standards. In addition to the Tribe’s secured funds and the eligible sources listed in Section 1g, the Tribe is well positioned to receive infrastructure financing through the Oregon Special Public Works Fund, Oregon Water/Wastewater Fund, Oregon Regional Solutions Infrastructure Fund, and U.S. Economic Development Administration programs to support these improvements.

| Table 1: Indicator | Tribe | Oregon | US |
| --- | --- | --- | --- |
| Median Household Income | $26,667 | $80,426 | $78,538 |
| Unemployment 2019-2023 | 9.2% | 3.3% | 3.3% |
| Poverty (all people) | 44.9% | 11.9% | 12.4% |
| Poverty Age <18 | 46.9% | 12.9% | 16% |

Source: 2023 5-Year US Census American Community Survey

2. COMMUNITY NEED AND COMMUNITY ENGAGEMENT: Community Need: 2.a. The Community’s Need for Funding: The CTGR community is very small, with just over 5,500 members. The median household income of Tribal members living on the Grand Ronde reservation is 33% of the statewide median income, and the poverty rate is over 3 times the statewide rate. Unemployment in the community is also much higher than the statewide rate. Tribal funds are limited, and dedicated to education, healthcare, and community support. EPA grant funding for Site cleanup and reuse will allow the Tribe to continue dedicating resources to these critical community needs. The grant will help the Tribe and local community by preparing the Site for new job opportunities and revenue generating uses through leases, business income, tourism spending, and destination events. Due to limited resources, the Tribe is unable to fund Site cleanup and reuse without grant assistance. Cleanup funding sources are limited, making the EPA Brownfield Cleanup grant a critical component of the project reuse plan.

2.b. Health or Welfare of Sensitive Populations: Homeless people are a significant sensitive population in the Target Area. In 2017, Clackamas County declared a state of emergency due to the lack of shelter for the growing homeless population after a woman died in a fire at a tent camp less than 2 miles from the Site. The population of unsheltered people rose from 43% in 2023 to 63% in 2025, and the number of homeless children also increased. In December 2025, emergency crews rescued homeless campers stranded in high water during flooding in Clackamas County. Unhoused people may seek shelter in vacant areas like the Site, where they may be exposed to contaminants and unsafe conditions in old buildings and along the river. Although the Site is secured, people have gained access. In January 2025, trespassers sheltering in one of the Site’s vacant buildings started a massive fire.

The health and welfare of the Target Area’s elderly and young residents are also at risk. 22% of Oregon City residents are under 18 and 14% are over 65. These groups may have underdeveloped or weakened immunity, making them more vulnerable to the health effects of contaminants. The young and elderly, as well as unhoused people, are also vulnerable to extreme heat. During a 2025 heat wave, Clackamas County emergency rooms and clinics recorded 101 heat‑related medical visits and Clackamas County investigated the death of a 55‑year‑old woman in Oregon City as potentially heat‑related.

This grant will remove contaminants, eliminating potential exposure of sensitive populations on and near the Site. Cleanup and reactivation of the Site will remove an attractive nuisance and will boost the local tax base allowing revenues to be directed toward addressing homelessness. The Site redevelopment plan will also increase greenspace, which will help with extreme heat events, and increase flood management capacity.

| 2.c. Greater Than Normal Incidence of Disease & Adverse Health Conditions: The most recent Clackamas County Health Assessment shows that cancer is one of the leading causes of preventable deaths in the county (Table 2). Clackamas County is in the worst 25% of Oregon counties for cancer rate among the Medicare population comprised mostly of people who are over 65 and younger people Table 2 Cancer type | Clackamas County State Percentile |
| --- | --- |
| All cancers | 78th |
| Melanoma | 99th |
| Breast Cancer | 75th |
| Childhood Cancers | 96th |

Source: NIH National Cancer Institute 2017-2021

with disabilities. The Oregon Health Authority found that Clackamas County’s 2018-2022 incidence rate for all cancers (443.6 per 100K) was higher than the state rate of 402.1 per 100K. Residents in the three census tracts closest to the Site are in the 73rd to 90th state percentiles for low life expectancy.

Known Site contaminants include carcinogens such as asbestos, polychlorinated biphenyls, petroleum constituents such as benzene and benzo(a)pyrene, and heavy metals. Contamination in surface soil and crumbling buildings at this large brownfield may become airborne as vapor or dust or be washed from the Site into the surrounding area, and onsite trespassers may come into direct contact with these contaminants. This grant will enable final cleanup of the site, removing these contaminants from the community and preparing the site for healthy reuse.

| Table 3 – Environmental Burden/Economic Indicator | Target Area* Percentile in US |
| --- | --- |
| Total Environmental Burden | 92nd |
| Air Pollution | 97th |
| Water Pollution | 89th |
| Toxics Release Inventory | 82nd |
| Risk Management Plan Sites | 77th |
| Housing Built Pre-1980 | 74th |
| Railways | 77th |
| Poverty | 54th |
| Housing Cost Burden | 67th |

2.d. Economically Impoverished/Disproportionately Impacted Populations: Target Area residents live near one of the largest brownfields in Oregon (the Site). They are also exposed to a high number of additional pollution sources, buildings built before 1980 that may have asbestos and lead paint, and a busy highway/ railroad. Target Area residents disproportionately share the negative environmental effects of these operations and environmental and land use policies. The US Agency for Toxic Substances and Disease Registry (ATSDR)11 ranks the environmental burden as “High” for the census tract where the Site is located and adjacent tracts, based on multiple risk factors. Table 3 shows the Site’s census tract is in the worst 3% to 26% of US census tracts for exposure to pollution. The Target Area also experiences a disproportionate economic burden. The area has more households living in poverty than over half of U.S. census tracts and has a higher housing cost burden (ratio of income to housing cost) than 67% of US census tracts.

While in operation, the Blue Heron Mill was identified by DEQ as a major source of hazardous pollutants and was identified for multiple violations related to its National Pollution Discharge Elimination System and Resource Conservation and Recovery Act (RCRA) permits due to releases of contaminants in wastewater discharges and exceedances of limits on hazardous materials generation and storage. The Site’s past RCRA reporting shows that ignitable and corrosive waste, arsenic, chromium, lead, mercury, solvents, and chloroform were handled on the Site.

This grant will help the Tribe address the residual contamination left on this large brownfield that is potentially impacting an already overburdened community. It will also spark economic activity bringing jobs and property value benefits to low income and housing-cost burdened residents.

Community Engagement:  2.e. Project Involvement and 2.f. Project Roles:

| Organization and Contact | Organization Mission | Specific Project Involvement or Assistance |
| --- | --- | --- |
| Citizen Involvement Committee of Oregon City – Jared Lyman, 503-496-1547, communications@orcity.org | Boosting public participation in local government by providing information, training, and communication channels to the City Commission. | CIC is made up of representatives of Oregon City’s neighborhood associations. CIC will share project information through their established communication networks. |
| Downtown Oregon City Association Juliana Allen, 503-802-1640, liz@downtown oregoncity.org | To build community and cultivate commerce in downtown Oregon City. | This non-profit organization focused on the revitalization of Oregon City’s 175-year-old downtown will assist with outreach and provide input to help align Site reuse plans with the downtown neighborhood. |
| Clackamas County Public Health Erika Zoller, 503-502-1243, ezoller@clackamas.us | Protecting and promoting the community's health by advancing racial health equity, building partnerships, and establishing culturally responsive systems. | The County Health Department will assist with outreach to sensitive populations and establishing metrics to track project outcomes. |
| Willamette Riverkeeper Heather King – 503-223-6418 heather@willametteriverkeeper.org | To protect and restore the Willamette River. | Willamette Riverkeeper will represent environmental interests in the project. |
| Oregon DEQ - Mark Pugh , 503-229-5587, pugh.mark@deq.state.or.us | Advancing environmental protection and justice for all communities and ecosystems in Oregon | The Tribe will continue to work closely with DEQ to ensure assessment and cleanup activities comply with state requirements and standards. |

2.g. Incorporating Community Input: Community outreach during the EPA grant project will be a continuation of the robust engagement already begun by the Tribe and project partners. At the start of the EPA grant, the Tribe will prepare an EPA grant-specific Public Involvement Plan (PIP) to guide and track outreach efforts specific to grant activities. The PIP will document methods for harnessing the experience, tools, methods, and networks established over the long history of community engagement around the former Blue Heron Mill. The PIP will include a schedule of grant-specific outreach events, methods for publicizing grant news and announcements in the local community and identify project partners and roles.

Community engagement specific to this grant began when the Tribe held a virtual public meeting on DATE?? to share the plan to apply for an EPA Brownfield Cleanup Grant. Community members attended the event to learn about and share ideas around how the grant can help shape and advance the Site’s revitalization plans. The Tribe will host a at least three additional grant-related public events during the grant term to inform the public and solicit input. The events will be held at key milestones which may include when news of the grant award is received, during cleanup, and when cleanup is complete. The Tribe is able to hold public meetings virtually or in person to accommodate community members with limited mobility. The Tribe can also record presentations for posting Tribal and partner websites. The Tribe will prepare signage for display during the project to inform the public about the activity and noting that it was funded by an EPA Brownfield Grant.

Project information will be shared with the Tribal and Target Area communities on at least a quarterly basis during the grant term via presentations at these events and/or through the Tribe’s newspaper Smoke Signals, press releases, fact sheets, the project-specific webpage on the Tribe’s website, the Tribe’s Facebook page, and through community partner networks, social media outlets, and events.

Community input will be gathered using tools including electronic polling and surveys at events, capturing input during presentations/public meetings, and from comments provided directly to the Tribe via website comments, emails, and phone calls. The Tribe will compile community input from these sources on a quarterly basis and develop responses for posting and publicizing via tools like Frequently Asked Questions posted on the Tribe’s website and fact sheets and articles posted at community-accessible locations addressing specific issues, questions, and suggestions. The Tribe’s responses to input will be summarized in the quarterly project progress reports and in communications with the community.

3. TASK DESCRIPTIONS, COST ESTIMATES, AND MEASURING PROGRESS:

3.a. Proposed Cleanup Plan: Cleanup of the Site will comprise: 1) excavating soil hot spots identified throughout the property (cleanup of Parcel 2 hot spots will be done with CTGR funding as prior use of EPA cleanup funding has made this parcel ineligible for further EPA cleanup funding); and 2) excavating contaminated soil as necessary to complete a planned ecological restoration project in the northern portion of the Site. All hot spot soils (estimated total of 20,000 yds3) will be transported to either a RCRA Subtitle D or C landfill for disposal. Ecological restoration contaminated soil (estimated total of 108,000 yds3) will be disposed at a facility yet to be determined in accordance with a DEQ Solid Waste Letter of Authorization. Following hot spot soil cleanup, confirmation soil sampling will be completed to confirm sufficient cleanup. As ecological restoration soil cleanup will expose underlying bedrock, confirmation soil sampling will not be feasible or necessary.

3.b., c, d, and e: Description of Tasks/Activities and Outputs: EPA grant funded activities are described below.

| TASK 1: PROJECT MANAGEMENT | Lead: CTGR assisted by QEP |  |  |
| --- | --- | --- | --- |
| Implementation: CTGR monitor project scope, schedule, budget, and compliance with grant terms and conditions including timely reporting and drawdowns. After grant award but prior to the start of the grant term, CTGR will procure a Qualified Environmental Professional (QEP) through an EPA procurement compliant process. Early procurement of the QEP will ensure that CTGR and the QEP can begin grant activities at the very start of the grant term. Supported by its QEP, CTGR will prepare an EPA compliant Request for Proposal (RFP) to select a remediation contractor. Project management activities also will include: 1) quarterly reporting; 2) annual financial reporting; 3) entries in the EPA Assessment, Cleanup and Redevelopment Exchange System (ACRES) database; and 4) grant closeout reporting. CTGR will attend two brownfield conferences during the grant term, but all conference fees and travel costs will be paid by CTGR. |  |  |  |
| # Schedule: CTGR will complete all quarterly and annual reporting on time. CTGR anticipates selecting a QEP prior to 10/1/26, and a remediation contractor prior to 3/1/27. CTGR will complete a grant closeout report within 90 days of end of the grant term. |  |  |  |
| # Outputs: Quarterly reports; EPA ACRES database updates at project milestones; annual financial reports; grant closeout report; and RFPs for QEP and remediation contractor procurement. |  |  |  |
| TASK 2: COMMUNITY ENGAGEMENT |  | # Lead: CTGR assisted by the QEP |  |
| # Implementation: 1) Prepare Public Involvement Plan (PIP); 2) Hold at least three community meetings (virtual or in-person) during the grant term and post recordings of virtual meetings on CTGR and partner websites; 3) Prepare outreach materials including fact sheets, press releases, website/Facebook page project updates, articles in CTGR’s Smoke Signals independent newspaper publish twice monthly in print and online, and signage explaining project activities; and 4) Solicit and respond to community input via electronic surveys, interactive community events such as workshops and charrettes, Q&A at outreach events, and calls and emails from community members to grant project representatives at the Tribe; document input and responses on Q&A summary sheets and in quarterly progress reports to EPA. |  |  |  |
| # Schedule: The PIP and initial fact sheet will be finalized in the first quarter of the grant term. Three public outreach events will be held at key project milestones. Press releases will also be prepared for project milestones and to publicize outreach events. CTGR has already established a project webpage on it’s website (https://www.grandronde.org/government/ economic-development-program/tumwata-village/) and will add news and documents as they become available throughout the grant term. Input and responses will be documented on at least a quarterly basis. |  |  |  |
| # Outputs: PIP; at least three community meetings held and notes/presentation materials developed; 2-3 project fact sheets and press releases/news articles; project updates on CTGR and partner websites; documentation of public input/questions and responses |  |  |  |
| TASK 3: CLEANUP |  |  | Lead: QEP directed by/reporting to CTGR |
| # Implementation: QEP: 1) Finalize ABCA and prepare Remedial Action Plan (RAP); 2) coordinate with DEQ under the Voluntary Cleanup Program; 3) prepare and obtain EPA approval of sampling and analysis plan (SAP)/quality assurance project plan (QAPP) for confirmation soil sampling; 4) complete all NHPA and endangered species cross cutters 5) prepare health and safety plan; 6) oversee/direct cleanup contractor during remedial action implementation; 7) conduct confirmation soil sampling in soil hot spot remedial action areas; and 8) prepare draft/final cleanup reports. # Cleanup Contractor: 1) Prepare all pre-work submittals (health and safety plan, traffic management plan, 1200C permit, etc.) for review/approval by CTGR/QEP; 2) Mobilize to Site and implement all required best management practices (erosion control measures, etc.); 3) Excavate and load all hot spot soils and transport to Hillsboro Landfill in accordance with the RAP; 4) Maintain all disposal documentation and provide to QEP; 5) Assist the QEP in collecting soil hot spot area confirmation soil samples; 6) Excavate and load all ecological restoration contaminated soils and transport to the facility identified in the DEQ-approved RAP; 7) Complete all post-cleanup Site restoration activities. |  |  |  |
| Schedule: Finalized ABCA and RAP by 3/1/27; Finalized SAP/QAPP by 5/1/27; Approved Contractor and QEP pre-remediation submittals by 6/1/27; Start remedial action by 6/15/27 and complete remedial action by 6/15/28; Complete final cleanup report by 9/30/28. |  |  |  |
| Outputs: Final ABCA; RAP; QAPP/SAP; HASPs and other pre-work submittals; Endangered Species Act and NHPA documentation; Draft/Final Cleanup Report. |  |  |  |

3.f. Cost Estimates: The budget below was prepared with the assistance of an environmental professional knowledgeable about Site conditions. The budget described is for EPA brownfield grant funding only (total of $4M). CTGR has the following leveraged funding sources to pay the balance ($3M) of the estimated $7M cleanup project described in this application: 1) $1M (secured) from 2022 Congressional Appropriations; 2) $500K (unsecured) in grant funding for cleanup from Business Oregon; and 3) $1.5M in CTGR funding (unsecured) (CTGR has been spending $1.5-$2M annually to further Site redevelopment and plans to continue to do so. The contractual budget assumes an average QEP hourly rate of $160/hour.

| Budget Categories | Project Tasks ($) |  |  |  |
| --- | --- | --- | --- | --- |
|  | Task 1 Project Management | Task 2 Community Engagement | Task 3 Cleanup | Total |
| Personnel, etc.* | $0 | $0 | $0 | $0 |
| Contractual (QEP) | $32,000 | $24,000 | $144,000 | $200,000 |
| Contractual (Cleanup Contractor) | $0 | $0 | $3,800,000 | $3,800,000 |
| Total Direct Costs | $32,000 | $24,000 | $3,944,000 | $4,000,000 |
| Total Indirect Costs | $0 | $0 | $0 | $0 |
| TOTAL BUDGET | $32,000 | $24,000 | $3,944,000 | $4,000,000 |

* CTGR will cover personnel, fringe benefits, travel, equipment, supplies, conference fees, and costs for DEQ oversight with CTGR funds. Further, CTGR will not seek compensation for indirect costs.

Task 1 - Project Management, Total $32,000: QEP Labor: $32,000 (200 hours x $160/hour).

Task 2 - Community Involvement, Total $24,000: QEP Labor: $24,000 (150 hours x $160/hour).

Task 3 - Cleanup, Total $3,944,000: QEP Total $144,000: QEP Labor: $128,000 (800 hours x 160/hour); Confirmation sample laboratory testing: $16,000 (50 samples @ $320/sample).

Remediation Contractor Total 3,800,000: Soil hot spot cleanup (nonhazardous): $1,881,000 (19,800 yd3 x $95/yd3); Soil hot spot cleanup (hazardous): $30,000 (200 yd3 x $150/yd3); Ecological restoration soil cleanup: $1,889,000 (41,000 yd3 x $46.07/yd3).

3.g. Plan to Measure and Evaluate Environmental Progress and Results:  When preparing the project RAP, CTGR and its QEP will develop a detailed schedule of key project milestones such as remediation contractor procurement, outreach event dates, cleanup start date, and cleanup completion date. At least monthly, CTGR will track and evaluate progress in achieving outputs and milestones against the RAP schedule. CTGR will monitor the project budget concurrently with tracking the schedule, on at least a monthly basis. CTGR will document project outputs, outcomes, and results in each quarterly progress report submitted to EPA and in EPA’s ACRES database. Anticipated outputs are described in Section 3b. Anticipated outcomes and results that CTGR will track include:

| Environmental Outcomes: - Volume of contaminated soil removed - Number of acres ecological restoration completed to improve habitat - Amount of energy savings from green remediation measures | Economic Outcomes: - Number of permanent and temporary jobs created - Number of acres of land readied for redevelopment - Increase in local property values and tax revenues - Amount of funding leveraged |
| --- | --- |

4. PROGRAMMATIC CAPABILITY AND PAST PERFORMANCE:

4.a. Organizational Structure and 4.b. Description of Key Staff: The CTGR operates under a representative government led by an elected nine-member Tribal Council, overseeing various departments and programs like Engineering and Planning, Economic Development, Cultural Resources, Education, Social Services, and Health. The Engineering and Planning Department, led by Ryan Webb, will lead cleanup grant implementation with support from multiple additional departments.

Ryan Webb, PE Engineering and Planning Manager with the CTGR is the Project Director for this grant.  Mr. Webb has 15 years of experience managing projects within the Portland Metro area, including the CTGR’s FY2021 EPA multi-purpose brownfield grant project. Mr. Webb also will receive significant support from Kristen Svicarovich, PE in all aspects of project implementation the same role Ms. Svicarovich fulfilled during implementation of CTGR’s FY2021 grant. Stacia Hernandez, Chief of Staff for CTGR, will coordinate all public and community outreach efforts and lead collaboration efforts with project partners. Ms. Martin is a CTGR member and has been employed by CTGR for over 16 years. Wendy Sparks, Grants Program Manager for CTGR, will assist with grant management, compliance, and reporting. Ms. Sparks has 20 years’ experience with federal grant projects. DeAnne Norton, Staff Accountant, will assist with budget tracking, documentation, reporting, and drawdowns. CTGR staff will coordinate with staff in the lands, natural resources, Tribal Historic Preservation Office, and other departments as needed.

4.c. Acquiring Additional Resources: CTGR has a procurement ordinance and policy governing purchases of goods and services that sets forth the competitive selection processes. The procurement policy requires compliance with any federal funding source requirements with respect to purchasing and program compliance. CTGR will comply with EPA’s solicitation clauses in the performance of this grant. The CTGR’s legal department reviews contracts and agreements and its procurement department facilitates purchase orders and payments. CTGR will utilize the required procurement procedures in selecting consultants and contractors to complete grant work.

Past Performance & Accomplishments:

4.d. Currently Has or Previously Received an EPA Brownfields Grant: CTGR was awarded an $800K FY2021 Brownfields Multipurpose Grant by the EPA.

4.d.(1) Accomplishments: Three primary FY2021 multi-purpose grant outputs achieved included: 1) To be completed

4.d.(2) Compliance with Grant Requirements: CTGR has successfully complied with all aspects of its Cooperative Agreement terms and conditions and work plan. All quarterly and annual reporting was completed on schedule and all project ACRES reporting was timely completed.

https://www.tumwatavillage.org/wp-content/uploads/2024/09/2023-0112-WM_GBD-Tumwata_Small.pdf

Conservatively assuming 2,500 part time (1,040 hrs/year) minimum wage ($16.30/hr) jobs

The Value of Brownfield Remediation | Journal of the Association of Environmental and Resource Economists: Vol 4, No 1

Cooling centers open throughout Clackamas County

https://louisvilleky.gov/sites/default/files/2020-12/louisvillefactsheet.pdf

2025 Point in Time Count

2017 Community Health Assessment Clackamas County Public Health Division

NIH National Cancer Institute 2017-2021

Oregon Health Authority

Policy Map

ATSDR Place and Health GRASP Database https://www.atsdr.cdc.gov/place-health/php/eji/eji-explorer.html

*Represented by Census Tract 41005022400 which includes the Site